## Sheet1
Schedule
| requirements | Date
| The system must be able read the student email addresses from a csv or txt file | Jan 29- Feb 11
| The system must be able to authenticate between student GitHub and UCL email address | Feb 12 - Feb 25
| The system should be able to authenticate one sutdent's accounts of GitHub classroom and Moodle Group | Feb 26- Mar11
| Auto grading the codeing assignments using unit test | Mar12 - Mar25
| checking coding assignments' similarity using MOSS | Mar 26 - April 11
| Configure GitHub Actions to run the unit tests when the code is changed | April 12 - April 25
| Deploy for COMP0035(computer system) which should be hosted within UCL infrastructure | April 26 - May 11
| Have a detailed documantation | May 11 - May25
| Finalise Report | May 26-June 16
EC | May 5th - June 16th